## Sheet1
Due Date | Days To Complete | Document Submission
2023-04-10 | 14 | Project planning and research proposal / chapter 1 (for feedback)
2023-04-24 | 8 | Project planning and research proposal / chapter 1 (for assessment)
2023-05-02 | 13 | Ethical clearance document
2023-05-15 | 18 | Research methodology (for feedback) /
2023-06-02 | 45 | Research methodology (for assessment) /
2023-07-17 | 87 | Literature review (for feedback)
2023-10-12 | 4 | Literature review (for assessment)
2023-10-16 | 14 | Demonstrations of projects (for assessment)
2023-10-30 | 0 | Documentation - all chapters (for feedback)

## Sheet2
Date | Activities | Person Responsible
SEMESTER 1
2023-02-23 | Lecture: Introduction and discussion of the process. | Prof E Taylor
2023-03-02 | Lecture: EndNote. | Me Linda Redelinghuys
2023-03-09 | Lecture: Academic writing and the correct handling of source referencing. | Dr A vd Merwe
2023-03-16 | Lecture: Research paradigms. | Prof R Goede
2023-03-23 | Lecture: Research paradigms (cont.) + | Prof E Taylor
Project planning and research proposal.
Recess 27 – 31 March
2023-04-06 | Lecture: Empirical research. | Prof T du Toit
2023-04-10 | Submission: Project planning and research proposal (for feedback). | Students
2023-04-11 | Feedback: Project planning and research proposal. | Supervisors
2023-04-20 | Lecture: Ethical clearance. | Prof L Drevin
2023-04-24 | Re-submission: Project planning and research proposal (for assessment). | Students.
Submission: Ethical clearance
2023-05-02 | Submission: Research methodology (for feedback) | Students
2023-05-09 | Feedback: Research methodology | Supervisors
2023-05-11 | Lecture: Literature review
2023-05-15 | Re-submission: Research methodology (for assessment). | Students
2023-06-02 | Submission: Literature review (for feedback) | Students
2023-06-15 | Feedback: Literature review | Supervisors
SEMESTER 2
Date | Activities | Person Responsible
2023-07-17 | Re-submission: Literature review (for assessment) | Students
2023-07-27 | Lecture: Quantitative and qualitative data analysis. | Dr J Liebenberg
2023-09-21 | Lecture: Project demonstration day. | Prof E Taylor
Recess 2 October – 6 October
2023-10-12 | Demonstrations of projects (for assessment). | All staff and students
2023-10-16 | Submission of complete documentation (for feedback). | Students
2023-10-23 | Feedback on complete documentation. | Supervisors
2023-10-30 | Re-submission: Complete documentation (for assessment). | Students
2023-11-20 | Final assessment completed. | Supervisors and moderators